## Sheet1
Task | Status | DueDate | DueAsDate | Estimate | %Complete | Description
Enhanced Alert Support | Complete | 01-Jul-19 | 2019-07-01 | 12 | 100% | Develop enhanced alerting capabilities needed to support Alert locations.
USGS Service Node | Complete | 05-Jul-19 | 2019-07-05 | 20 | 100% | Develop node to read the data from the USGS Water Watch data repository
GLOS Buoy Service Node | Active | 01-Aug-19 | 2019-08-01 | 20 | 20% | Develop a nde to read the latest Buoy data from the GLOS Buoy System