## Sheet1
Task | Status | DueDate | DueAsDate | Estimate | %Complete | Description
Location Enhancemets to Events | Complete | 01-Jun-19 | 2019-06-01 | 32 | 100% | Enhance all VDAB events to support GPS location.
Enhanced Alert Support | Complete | 01-Jul-19 | 2019-07-01 | 12 | 100% | Develop enhanced alerting capabilities needed to support Alert locations.
USGS Service Node | Complete | 05-Jul-19 | 2019-07-05 | 20 | 100% | Develop node to read the data from the USGS Water Watch data repository
500,000 Event Load Test | Complete | 01-Aug-19 | 2019-08-01 | 20 | 100% | Complete load and query performance test for 500,000 multi parameter metric events.
NDBC Buoy Service Node | Complete | 01-Aug-19 | 2019-08-01 | 20 | 100% | Develop a nde to read the latest Buoy data from the NDBC.
Complete Great Lakes Watershed | Complete | 15-Aug-19 | 2019-08-15 | 10 | 100% | Complete the development of the Great Lakes data model including all lakes
Server Migration to AWS | Complete | 15-Aug-19 | 2019-08-15 | 10 | 100% | Migrate reporting and alert support features of Mirro1 to AWS
Server Backup Implementation | Complete | 15-Aug-19 | 2019-08-15 | 10 | 100% | Implement a server backup and recover strategy.
Production Monitoring | Complete | 01-Sep-19 | 2019-09-01 | 16 | 100% | Implement comprehensive production server monitoring
WQDataLive Service Node | Completed | 12-Sep-19 | 2019-09-12 | 20 | 100% | Develop a node to read data from the WQDataLive data repository
HTTPS Web Support | Completed | 15-Oct-19 | 2019-10-15 | 20 | 100% | Develop complete support for using HTTPS for Rest APIs and maps.
Integrated Units Conversion | Scheduled | 01-Feb-20 | 2020-02-01 | 40 | 50% | Add integrated support of metric unit conversion.
5 Million Event Load Test | Scheduled | 01-Feb-20 | 2020-02-01 | 30 |  | Complete load and query performance test for 5,000,000 multi parameter metric events.
Hobolink Service Node | Active | 15-Jan-20 | 2020-01-15 | 48 | 80% | Develop a node for reading data directly from Hobolink
Location Support for MongoDB | Proposed | 15-Apr-20 | 2020-04-15 | 80 |  | Enhance the VDAB Mongo DB persistence to include Geo location support.
Data Certification Support | Proposed | 15-Apr-20 | 2020-04-15 | 120 |  | Develop complete support for data certification
Note on A2: Author:
Note on A3: Author: