## Sheet1
Task | Status | DueDate | DueAsDate | Estimate | %Complete | Description
USGS Map Page | Complete | 21-Jul-19 | 2019-07-21 | 20 | 100% | Develop a map page highlighting all USGS Flow data
Alerts Widget | Complete | 01-Aug-19 | 2019-08-01 | 20 | 100% | Develop a widget that displays current alerts and allows selection of an Alert for more details.
Alerts Detail Page | Active | 01-Aug-19 | 2019-08-01 | 12 | 20% | Develop an alert detail page including a map of the location.
Alerts List page | Scheduled | 15-Aug-19 | 2019-08-15 | 20 |  | Develop a page that allows searching and selecting all existing alerts.