## Sheet1
Task | Status | DueDate | DueAsDate | Estimate | %Complete | Description
Enhanced Alert Support | Completed | 01-Jul-19 | 2019-07-01 | 12 | 100% | Develop enhanced alerting capabilities needed to support Alert locations.
HTTPS Web Support | Completed | 15-Oct-19 | 2019-10-15 | 20 | 100% | Develop complete support for using HTTPS for Rest APIs and maps.
Integrated Units Conversion | Completed | 01-Feb-20 | 2020-02-01 | 40 | 100% | Add integrated support of metric unit conversion.
Hobolink Service Node | Completed | 15-Jan-20 | 2020-01-15 | 48 | 100% | Develop a node for reading data directly from Hobolink
Integrated MQTT Messaging | Completed | 15-Mar-20 | 2020-03-15 | 100 | 100% | Enhance MQTT integration so that all events are published using a standard JSON format
Enhanced Integrated Dashboards | Active | 15-Jun-20 | 2020-06-15 | 60 | 80% | Add integerated support for web dashboards including charts and maps
Automated Dataset Sync | Active | 15-Jul-20 | 2020-07-15 | 80 | 20% | Support automated data recovery and synchronization between backend servers.
Data Certification Support | Proposed | 15-Aug-20 | 2020-08-15 | 120 |  | Develop complete support for data certification
Location Support for MongoDB | Proposed | 15-Sep-20 | 2020-09-15 | 80 |  | Enhance the VDAB Mongo DB persistence to include Geo location support.
Note on A2: Author: