## Sheet1
Task | Status | DueDate | DueAsDate | Estimate | %Complete | Description
Text Data Queries | Completed | 10-Jan-20 | 2020-01-10 | 20 | 100% | Support text queries of the latest station data. Text the station path to 216-600-0212
Ploting Widgets for Dashboards | Completed | 01-May-20 | 2020-05-01 | 20 | 100% | Develop a series of dashboard widgets for assembling plotting investigation pages.
Map Widgets for Dashboards | Completed | 15-May-20 | 2020-05-15 | 20 | 100% | Develop generalized map support widgets with customizable pin icons and data.
Comparing River Flows Page | Active | 10-Jun-20 | 2020-06-10 | 10 | 80% | Develop a page for comparing the historical river flows for any two Great Lakes stations
Generalized Data Plotting Page | Active | 10-Jun-20 | 2020-06-10 | 75 | 80% | Develop a flexible GLDW data plotting page supporting any GLDW data.
Enhanced Buoy Data Map | Proposed | 01-Jul-20 | 2020-07-01 | 15 | 10% | Develop enhanced buoy map display features including graphical wind direction and metric display.