## Sheet1
Task | Status | DueDate | DueAsDate | Estimate | %Complete | Description
Wifi Uplink Radio | Complete | 01-Jul-19 | 2019-07-01 | 20 | 100% | Develop capabilities to use WiFI as an uplink between the Mayfly and the PI3-VDAB hub
Integrate Depth Sensor | Complete | 15-Aug-19 | 2019-08-15 | 10 | 100% | Select, integrate and test a Depth Sensor with the standalone Mayfly Data Logger
Integrate Temperature Sensor | Complete | 15-Aug-19 | 2019-08-15 | 10 | 100% | Select and integrate a water temperature sensor
Complete River Monitoring Station | Completed | 01-Feb-20 | 2020-02-01 | 80 | 100% | Complete weatherproofing and packaging of a complete water monitoring station
Deploy River Monitoring Station | Completed | 01-Mar-20 | 2020-03-01 | 80 | 100% | Deploy a water monitoring station at the Watershed Stewardship Center
Build Station Dashboard | Completed | 01-Apr-20 | 2020-04-01 | 80 | 100% | Build a dashboard for the deployed monitoring station.
LoRa Radio Support | Proposed |  |  |  |  | Develop support for LoRa communications to a PI3 hub
4G Radio Support | Proposed |  |  |  |  | Develop support for 4G communications form the PI3 hub or integrated monitoring station.
Mayfly Control Node | Proposed |  |  |  |  | Develop a control node for simplifying setup and control of a Mayfly Data Logger