## Sheet1
Task | Status | DueDate | DueAsDate | Estimate | %Complete | Description
USGS Map Page | Complete | 21-Jul-19 | 2019-07-21 | 20 | 100% | Develop a map page highlighting all USGS Flow data
Alerts Widget | Complete | 01-Aug-19 | 2019-08-01 | 20 | 100% | Develop a widget that displays current alerts and allows selection of an Alert for more details.
Alerts Detail Page | Complete | 01-Aug-19 | 2019-08-01 | 12 | 100% | Develop an alert detail page including a map of the location.
NDBC Buoy Map - PreLoaded | Complete | 15-Aug-19 | 2019-08-15 | 10 | 100% | Develop a mapping page that displays the NDBC buoy data using a static Google fusion document.
NDBC Buoy Maps - Live | Complete | 15-Sep-19 | 2019-09-15 | 20 | 100% | Develop a mapping page that displays the NDBC buoy data directly in a google map
USGS State Map | Complete | 15-Oct-19 | 2019-10-15 | 20 | 100% | Develop a USGS map that can display data for any state.
Alerts List page | Proposed |  |  | 20 |  | Develop a page that allows searching and selecting all existing alerts.