## Sheet1
Task | Status | DueDate | DueAsDate | Estimate | %Complete | Description
Location Enhancemets to Events | Complete | 01-Jun-19 | 2019-06-01 | 32 | 100% | Enhance all VDAB events to support GPS location.
Enhanced Alert Support | Complete | 01-Jul-19 | 2019-07-01 | 12 | 100% | Develop enhanced alerting capabilities needed to support Alert locations.
USGS Service Node | Complete | 05-Jul-19 | 2019-07-05 | 20 | 100% | Develop node to read the data from the USGS Water Watch data repository
500,000 Event Load Test | Active | 01-Aug-19 | 2019-08-01 | 20 | 40% | Complete load and query performance test for 500,000 multi parameter metric events.
GLOS Buoy Service Node | Active | 01-Aug-19 | 2019-08-01 | 20 | 20% | Develop a nde to read the latest Buoy data from the GLOS Buoy System
5 Million Event Load Test | Scheduled | 01-Sep-19 | 2019-09-01 | 30 |  | Complete load and query performance test for 5,000,000 multi parameter metric events.
Note on A2: Author:
Note on A3: Author: